## IP Translation
IP Translation Team
No. | Technology / IP | TRL (1-9) | Type | Service Target | Targeted Market | Technical Lead | Engineer | Current Status | Timeline (Completion Date) | Next Action Items | By When | Date of Last Entry | Remarks
1 | Privacy-preserving data fusion | 7 | IP licensing | Data privacy protection platform | Health-care Education F&B | Geong Sen | Jason Loh / Shuwei/ Janathan | POC ready (ie. SATS PoC in Sept. 2019) | 1. work with Soo Kiat's team to engage SATS for POC (Sept. 2019) 2. Get ready session with MOH | 1. To get Legal clearance on POC T&C | End Aug'19 | 2019-08-23
2 | Private distributed machine learning | 2 | New product feature | Data privacy protection platform |  | Geong Sen | Varsha, Randy, Edward | Modules for logistic regression and linear regression without privacy-preservation were developed. Logistic regression use case integrated to PrivateLink. Starting research on privacy-preserving distributed ML. Exploring DP and MPC techniques. | To be POC ready by Nov 2019 for logistic and linear regression. | Define use case for linear regression | Sept'19 | 2019-09-03
3 | Automated evasive malware analysis | 4 | Enhancement of existing product | SEG |  | Pete Goi | Janathan & Prof. FYP student | - Based on the paper, the results of PDF morpher is yet to reproduce any Evasive and Malicious PDF. - Found 50+ known malwares in the wild that are malicious and able escape detection by TW SEG V.8.1.3.11605 | Nov-19 | - Re-confirmed that Hung's provided morphed sample is not malicious by Phil team. - We will engage with Phil team to explore the characteristic of the 50+ known evasive malwares and why it is evasive in current TW SEG V.8.1.3.11605 - At the same time, we are still exploring ways to create evasive pdf malwares | Sept'19 | 2019-08-13
4 | Proof of data residency | 4 | New product feature | DBProtect |  | Xu Jia | Liu Yuancheng?\ | Developing GUI Ready for PoC (ie. NRF demo) | To be ready for POC by Oct 19 | To prep for NRF review demo. To share with DBProtect Engr | 2019-08-19 | 2019-08-27
5 | Quantum-safe secure communications | 4 | New product | Quantum-resistant VPN & TLS service |  | Xu Jia | Gao Yiwen Shijing | Implementing DPDK version of IPSec. The example is given by DPDK. ARP passthrough is resolved. IP fragmentation reassemble problem is not resolved. Currently, we require users to adjust MTU size of their devices to 1400. Throughput with encryption: 300 mbps The experiment is done using four VMs on one machine. Throughput is measured by netperf using UDP stream. MHA Beacon proposal (ie. $118k from NUS-SIngtel CorpLab) | To have a prototype ready to be presented to MHA/CSIT by Aug 2019 | 1. To engage CSIT, DSTA & IMDA 2. Resolve IP fragmentation reassemble problem by the end of August. 3. Start implementing Internet Key Exchange (or new protocol) after the IP fragmentation problem is resolved. Reference implementation can be found on fd.io VPP. The estimation time is one to three months. Needs to discuss the specs if a new protocol should be designed. | 2019-08-30 | 2019-08-23
6 | Privacy-preserving DLP | 4 | New Product feature | SEG |  | Geong Sen | Jason Loh | WIP (KIV) Simply Demo ready | TBD |  |  | 2019-08-23
7 | Anomaly Detection ML model for DBProtect | 2 | Enhancement of existing product | DBProtect |  | Geong Sen | Shaowen Randy Edward | finishing initial concept realization Waiting DB log / data 5 Sept. 2019 | To have a prototype ready by Nov 2019 | 1. Liaise with Dbprotect team on usage and effectiveness 2. Research on supplementary ideas to enhance the protoype | 2019-11-01 | 2019-09-03
8 | Secure IoT Software Supply Chain | 7 | New product feature | Singtel IoT Sense |  | Wong Jun Wen | Liu Yuancheng | On-going POC (with Singtel IoT) started in Apr 2019. Added gateway sensor sensor read program(app/web based program.) Receive from Vendor: UWB (ie. base-station) and doc. | To be ready for productization on Oct 2019 | Manoj team engaging device vendors for access to firmware. | Aug'19 | 2019-08-27
9 | Distributed IoT device fingerprinting | 6 | New product feature | MSS - IoT asset discovery |  | Dinil | Rishi | POC ready | To discuss and agree on IoT MSS roadmap by May 2019 | 1. Discussed with NCS Product R&D (Sook Fong) to get UNIFAI use cases. 2. Awaiting confirmation from James | Jun'19 | 2019-08-13 | De-prioritised, as the team is still looking for valid business case.
10 | IoT network anomaly detection | 5 | New product feature |  |  | Dinil / Vinay | Rishi | Implementation of solution | To be POC ready by Nov 2019 | Demonstrate prototye to Singtel and NCS teams | 2019-09-01 | 2019-08-13
11 | IoT firmware attestation (Protocol) | 5 | New product feature | Singtel IoT Sense |  | Wong Jun Wen | Liu Yuancheng | On-going POC (with Singtel IoT) started in Apr 2019 | To be ready for productization on Oct 2019 | Manoj team engaging device vendors for access to firmware. | Aug'19 | 2019-08-27
12 | Device localization | 4 | New product feature | Singtel IoT Sense |  | Wong Jun Wen | Liu Yuancheng | WIP | To be ready for POC by Aug 2019 | Is this part of IoT PoC scope? Cross check with JW. |  | 2019-08-27 | XJ will check with JW
13 | Enhancement of OT security cyber range platform | 4 | Enhancement of existing product | CSI – OT Training |  | Pete Goi / Wong Jun Wen | Liu Yuancheng | Studying the existing testbed to enhance the platform. Implemented the fake data injection attack and man in the middle attack. | Deliver by Dec 2019 | Initial demo on the ehnanced platform. Add more attack situation based on Shantanu's design. | 2019-10-01 | 2019-08-27 | $100k ~ 3days OT class