## IP Translation
IP Translation Team
No. | Technology / IP | TRL (1-9) | Type | Service Target | Targeted Market | Technical Lead | Engineer | Current Status | Timeline (Completion Date) | Next Action Items | By When | Date of Last Entry | Remarks
1 | Privacy-preserving data fusion | 7 | IP licensing | Data privacy protection platform |  | Geong Sen |  | POC ready | 1. work with Soo Kiat's team to engage STB for POC 2. To find use case within health-care industry | 1. To get Legal clearance on POC T&C | End Aug'19 | 2019-08-13
2 | Private distributed machine learning | 5 | New product feature | Data privacy protection platform |  | Geong Sen |  | Identification of use case | To be POC ready by Nov 2019 | Look for use case |  | 2019-08-13
3 | Automated evasive malware analysis | 4 | Enhancement of existing product | SEG |  | Pete Goi |  | - Based on the paper, the results of PDF morpher is yet to reproduce any Evasive and Malicious PDF. - Found 50+ known malwares in the wild that are malicious and able escape detection by TW SEG V.8.1.3.11605 | Nov-19 | - Re-confirmed that Hung's provided morphed sample is not malicious by Phil team. - We will engage with Phil team to explore the characteristic of the 50+ known evasive malwares and why it is evasive in current TW SEG V.8.1.3.11605 - At the same time, we are still exploring ways to create evasive pdf malwares | Sept'19 | 2019-08-13
4 | Proof of data residency | 4 | New product feature | DBProtect |  | Xu Jia | Liu Yuancheng | Developing GUI | To be ready for POC by Oct 19 | To prep for NRF review demo. To share with DBProtect Engr | 2019-08-19 | 2019-08-09
5 | Quantum-safe secure communications | 4 | New product | Quantum-resistant VPN & TLS service |  | Xu Jia |  | WIP | To have a prototype ready to be presented to MHA/CSIT by Aug 2019 | To addd 1 more feature to the platform To engage CSIT, DSTA & IMDA | 2019-08-19 | 2019-08-13
6 | Privacy-preserving DLP | 4 | New Product feature | SEG |  | Geong Sen |  | WIP
7 | ML model for DBProtect
8 | Secure IoT Software Supply Chain | 7 | New product feature | Singtel IoT Sense |  | Wong Jun Wen | Liu Yuancheng | On-going POC (with Singtel IoT) started in Apr 2019 | To be ready for productization on Oct 2019 | Manoj team engaging device vendors for access to firmware. | Aug'19 | 2019-04-09
9 | Distributed IoT device fingerprinting | 6 | New product feature | MSS - IoT asset discovery |  | Dinil |  | POC ready | To discuss and agree on IoT MSS roadmap by May 2019 | 1. Discussed with NCS Product R&D (Sook Fong) to get UNIFAI use cases. 2. Awaiting confirmation from James | Jun'19 | 2019-08-13 | De-prioritised, as the team is still looking for valid business case.
10 | IoT network anomaly detection | 5 | New product feature |  |  | Dinil / Vinay |  | Implementation of solution | To be POC ready by Nov 2019 | Demonstrate prototye to Singtel and NCS teams | 2019-09-01 | 2019-08-13
11 | IoT firmware attestation | 5 | New product feature | Singtel IoT Sense |  | Wong Jun Wen | Liu Yuancheng | On-going POC (with Singtel IoT) started in Apr 2019 | To be ready for productization on Oct 2019 | Manoj team engaging device vendors for access to firmware. | Aug'19 | 2019-04-25
12 | Device localization | 4 | New product feature | Singtel IoT Sense |  | Wong Jun Wen | Liu Yuancheng | WIP | To be ready for POC by Aug 2019 | Is this part of IoT PoC scope? Cross check with JW. |  | 2019-04-25 | XJ will check with JW
13 | Enhancement of OT security cyber range platform | 4 | Enhancement of existing product | CSI – OT Training |  | Pete Goi / Wong Jun Wen | Liu Yuancheng | Studying the existing testbed to enhance the platform. | Deliver by Dec | Initial demo on the ehnanced platform | 2019-10-01 | 2019-07-26